## Project Description
Project One Pager
Project Name: | The PMzone Digital Simulation Board Game | Project Manager: | Hamutal Weisz
Client Name: | PMzone Ltd. | Sponsor Name:
Project General Description |  | Priority and Estimation
Develop an online Project Management game – based on the PMzone simulation board game, to allow participants to experience the challenges of managing projects while learning key elements in project management and improving their overall project management skills. |  | Project Priority: High (COVID-19 is an additional trigger) Estimated Duration: 5 Months Estimated Budget: $40,000 (not including Go-Live & Support)
Why?
In the last few decades there is a growing trend in business and social organizations to manage by projects. The modern project management organizations deal with high levels of uncertainty and complexity and traditional education methods of project management are simply not enough anymore. Projects are heterogeneous by nature and require an understanding of a wide range of topics as well as interpersonal and soft skills. The actual complexities involved in managing initiatives and making decisions on an array of interrelated issues, under uncertain conditions, call for a simulation tool that will enable prospective – and present project managers, to experience the practice of managing projects in a sandbox environment. The PMzone simulation board game is a serious game and is complex. Learning how to play the game is not easy and players struggle with all the rules implemented in this game. Transforming the physical game to a digital game will enable a friendly, guided platform that will assist players to learn and to play the game and therefore, to generate greater value and faster. Also, playing the physical game is suitable for small groups of players sitting together around tables in one room, and as such is not very scalable. The digital game will allow a large number of players to play simultaneously from anywhere in the world.
What will happen if the project is not implemented?
If the physical board game is not developed as a digital game, simulating project management using the PMzone simulation board game will remain confined to classrooms in small groups. The business model would rely mostly on local training provided directly by PMzone Ltd. or by our business partners. This model is difficult to implement and to scale.
Goals and Objectives
Goal | Objectives | Success Benchmark
Generate revenue from automatic services | Develop a tool for self-learning in project management | Have a digital project management simulation tool by the beginning of the next academic year
| Market the tool in academic institutions around the world | Secure 3 new academic institutions in the first year and then 4 more each year
| Market the tool in organizations and companies around the world | Secure 3 new companies in the first year and then 4 more each year
Scale training activities | Increase training activities in Israel | Increase training activities from existing clients by 40% Increase training activities from new clients by 20%
| Provide worldwide training activities | Increase training activities around the world by 20% each year
Create international reputation | Present at international conferences
Deliver training activities in person at a company from abroad
Advertise the company in magazines and websites in the field of project management
Stakeholders and Benefits
Stakeholder |  | Benefits to the Stakeholder
Vered – Local Academic representative |  | Adding value to academic programs Receiving recognition as an innovative professor Raising the reputation of the academic institution
Shai – EU Academic representative
Yael – US Academic representative
Joe – Partners’ representative |  | Creating differentiation from competitors Achieving a competitive advantage in the market Creating an additional revenue stream Creating a funnel to sell additional services
Assumptions and Constraints |  | Critical Success Factors
The game will be played on tablets or desktop computers (medium to large screens). |  | The game will allow for a synchronous multiplayer environment.
The game will be developed for the web. |  | The game will support hundreds of players simultaneously.
Time to market must be before the start of the coming academic year in September 2021. |  | The game will support effortless setup by the instructor.
The game will be developed in English however the development should allow translation to different languages. |  | The game will be as self-explanatory as possible so that it can be played without professional guidance.
The game will use the graphic design of the physical board game unless a different design offer would be feasible for the MVP. |  | The game will provide a great gaming experience.

## Requirements and Priorities
* | Requirements and Priorities
# | Requirement | Requirement Date | Priority | Priority Date
1 | Implement game mechanics, elements, and assets according to the game design document (GDD) | 2021-03-11 | Must Have | 2021-03-11
2 | Support a multi tables game with multi players assigned to a table (program) | 2021-03-11 | Must Have | 2021-03-11
3 | Manage user roles with different permissions (Admin, Instructor, PM Player) | 2021-03-11 | Must Have | 2021-03-11
4 | Support the PMO player in each table | 2021-03-11 | Won’t Have | 2021-03-11
5 | Develop basic game reports | 2021-03-11 | Must Have | 2021-03-11
6 | Develop advanced game reports and dashboards | 2021-03-11 | Should Have | 2021-03-11
7 | Provide in-game alerts, messages, and tooltips | 2021-03-11 | Must Have | 2021-03-11
8 | Implement game route including gates, milestones, known tasks, unknown tasks, constraints and risks | 2021-03-11 | Must Have | 2021-03-11
9 | Implement game currencies (resources and money) | 2021-03-11 | Must Have | 2021-03-11
10 | Implement project sheet which includes known tasks that needs to be planned before and during the game | 2021-03-11 | Must Have | 2021-03-11
11 | Implement game cards including unknown tasks, constraints, risks, and delays | 2021-03-11 | Must Have | 2021-03-11
12 | Implement dependent tasks (known and unknown) | 2021-03-11 | Should Have | 2021-03-11
13 | Implement special action cards | 2021-03-11 | Should Have | 2021-03-11
14 | Implement gate control check resulting in one of four outcomes: good to go, delay, return, cancel | 2021-03-11 | Must Have | 2021-03-11
15 | Implement game reset/start over when gate control fails, or player is out of money/resources | 2021-03-11 | Must Have | 2021-03-11
16 | Implement milestones and reward players with money and resources according to each milestone terms | 2021-03-11 | Must Have | 2021-03-11
17 | Implement value that players earn when completing tasks in the game | 2021-03-11 | Must Have | 2021-03-11
18 | Send game summary reports to instructors immediately after each game | 2021-03-11 | Should Have | 2021-03-11
19 | Send game summary reports to players immediately after each game | 2021-03-11 | Should Have | 2021-03-11
20 | Send periodic usage reports to admins | 2021-03-11 | Should Have | 2021-03-11
* | Requirements for PM Players
21 | Allow players to register to a game event | 2021-03-11 | Must Have | 2021-03-11
22 | Allow players to plan a project within the game | 2021-03-11 | Must Have | 2021-03-11
23 | Allow players to execute tasks (known and unknown) and earn value to their project | 2021-03-11 | Must Have | 2021-03-11
24 | Allow players to delay a task (known and unknown) | 2021-03-11 | Must Have | 2021-03-11
25 | Allow players to execute a constraint when they land on a constraint space on the route | 2021-03-11 | Must Have | 2021-03-11
26 | Allow players to execute a risk when they land on a risk space on the route | 2021-03-11 | Must Have | 2021-03-11
27 | Allow players to execute several known tasks in one turn | 2021-03-11 | Won’t Have | 2021-03-11
28 | Allow players to trade unknown tasks with other players | 2021-03-11 | Won’t Have | 2021-03-11
29 | Allow players to purchase more resources using their money when other players are playing | 2021-03-11 | Must Have | 2021-03-11
30 | Allow players to replace resources based on their value | 2021-03-11 | Must Have | 2021-03-11
31 | Allow players to purchase more resources or replace resources during their turn for double their value | 2021-03-11 | Must Have | 2021-03-11
32 | Allow players to get an extra one-time budget if they run out of resources/money | 2021-03-11 | Must Have | 2021-03-11
33 | Allow players to start game over when they are out of resources/money | 2021-03-11 | Must Have | 2021-03-11
34 | Allow players to start game over when their project is canceled in the gate control | 2021-03-11 | Must Have | 2021-03-11
35 | Allow players to view their game stats including available money and resources, earned value, known and unknown tasks completed, tasks delayed, constraints and risks executed, milestones and gates passed, position on the board, time into play and time remaining | 2021-03-11 | Must Have | 2021-03-11
36 | Allow players to view their game summary report at game end | 2021-03-11 | Must Have | 2021-03-11
37 | Allow players to video chat within the game | 2021-03-11 | Should Have | 2021-03-11
38 | Allow players to switch programs and projects between them | 2021-03-11 | Won’t Have | 2021-03-11
39 | Allow players to create programs and projects | 2021-03-11 | Won’t Have | 2021-03-11
* | Requirements for Instructors
40 | Allow instructors to schedule a game event | 2021-03-11 | Must Have | 2021-03-11
41 | Allow instructors to initiate a game event | 2021-03-11 | Must Have | 2021-03-11
42 | Allow instructors to invite other instructors to assist in a game | 2021-03-11 | Won’t Have | 2021-03-11
43 | Allow instructors to invite players to a game event | 2021-03-11 | Must Have | 2021-03-11
44 | Allow instructors to notify players on a game event | 2021-03-11 | Must Have | 2021-03-11
45 | Allow instructors to import players | 2021-03-11 | Must Have | 2021-03-11
46 | Allow instructors to assign players to programs (tables) and projects (manually and automatically) | 2021-03-11 | Must Have | 2021-03-11
47 | Allow instructors to re-assign players to different programs (tables) and projects during the game | 2021-03-11 | Won’t Have | 2021-03-11
48 | Allow instructors to view future game schedule | 2021-03-11 | Must Have | 2021-03-11
49 | Allow instructors to view previous game schedule | 2021-03-11 | Should Have | 2021-03-11
50 | Allow instructors to view game reports | 2021-03-11 | Must Have | 2021-03-11
51 | Allow instructors to join tables as a viewer during a game event | 2021-03-11 | Could Have | 2021-03-11
52 | Allow instructors to open support tickets | 2021-03-11 | Must Have | 2021-03-11
53 | Allow instructors to create programs and projects | 2021-03-11 | Won’t Have | 2021-03-11
54 | Allow instructors to launch competition events between instructors or players | 2021-03-11 | Won’t Have | 2021-03-11
55 | Allow instructors to select game level | 2021-03-11 | Won’t Have | 2021-03-11
* | Requirements for Admins
56 | Allow admins to create accounts | 2021-03-11 | Must Have | 2021-03-11
57 | Allow admins to create programs and projects (manually or import) | 2021-03-11 | Must Have | 2021-03-11
58 | Allow admins to assign programs to accounts | 2021-03-11 | Must Have | 2021-03-11
59 | Allow admins to create instructors and assign them to accounts | 2021-03-11 | Must Have | 2021-03-11
60 | Allow admins to set player limit and period | 2021-03-11 | Must Have | 2021-03-11
61 | Allow admins to create generic players and assign them to instructors (manually or import) | 2021-03-11 | Must Have | 2021-03-11
62 | Allow admins to generate usage reports | 2021-03-11 | Must Have | 2021-03-11
63 | Allow admins to setup game levels | 2021-03-11 | Won’t Have | 2021-03-11
64 | Allow admins to customize milestones’ terms | 2021-03-11 | Won’t Have | 2021-03-11
65 | Allow admins to customize gates’ terms | 2021-03-11 | Won’t Have | 2021-03-11
66 | Allow admins to customize unknown tasks’ cost (money and resources) and value | 2021-03-11 | Won’t Have | 2021-03-11

## Project Lifecycle
Project Lifecycle
Project Stage | Main Tasks in Stage | Main Deliverables in Stage | Main Milestones in Stage | Main Controls in Stage
Project Planning | Specify requirements Plan the project Prepare for development | Project Compass Document Project Plan | Compass document approved Project plan approved Project planning phase completed | Perform a peer review of the compass document Approve project plan
Design Game | Specify functional requirements Specify technical requirements Create wireframe mockups Design UI/UX | GDD (Game Design Document) Visual Design Document | Functional requirements approved Technical requirements approved Wireframe mockups approved Visual design approved Game design phase completed | Conduct DR (design review) with a focus group
Develop Game | Create development plan Develop Admin’s functionalities Develop Instructors’ functionalities Develop Players’ functionalities | Development Plan Development Environment | Development plan approved Game functionalities developed Game development phase completed | Approve development plan Perform development tests
Test Game | Create test plan & scenarios Perform Admin’s functional tests Perform Instructors’ functional tests Perform Players’ functional tests Perform UI/UX tests Perform technical tests | Test Plan Test Environment Test Reports | Test plan approved Functional tests completed UI/UX tests completed Technical tests completed Game testing phase completed | Approve test plan Review test reports
Go Live & Support | Plan the operation Plan the marketing Develop training materials Develop marketing materials Transfer game to hosting Perform Go-Live tests | Operation Plan Marketing Plan Training Guide Marketing Messages Digital Game Go-Live Test Reports | Operation plan approved Marketing plan approved Training guide approved Marketing messages approved Go-Live tests completed Go-Live & Support phase completed | Approve operation plan Approve marketing plan Approve training guide Approve marketing messages Review test reports

## Roles and Responsibility Matrix
Roles and Responsibility Matrix
Milestone/Deliverable | Project Manager | Focus Group Leader | Development Team Leader | Design Team Leader | QA Leader | Technical Consultant | Marketing Consultant
Project Compass Document | 1,6 | 2,6 |  |  | 3
Project Plan | 1,6 | 2,6 | 3 | 3 | 3 | 4 | 4
GDD (Game Design Document) | 2,6 | 2,6 | 1 |  | 3 |  | 4
Visual Design Document | 2,6 | 2,6 |  | 1 | 3 |  | 4
Development Plan | 2 | 2 | 1 |  | 4 | 3,6
Development Environment | 2 |  | 1 |  |  | 4
Test Plan | 2,6 | 2,6 |  |  | 1 | 3
Test Environment | 2 |  | 2 |  | 1
Test Reports | 2,6 | 2,6 | 2 |  | 1 | 4
Operation Plan | 1,6 | 2,6 |  |  |  |  | 3
Training Guide | 1,6 | 2,6 |  |  |  |  | 3
Production Environment | 5,6 | 5,6 | 1 |  |  | 2
Go-Live Test Reports | 2,6 | 2,6 | 1 |  | 3 | 3

## Involvement and Impact Matrix
Involvement and Impact Matrix
Stakeholder | Role in the Project | Areas of Responsibilities | Involvement | Impact | Gap
Vered | Local Academic representative |  | 4 | 4 | 0
Shai | EU Academic representative |  | 3 | 4 | 1
Yael | US Academic representative |  | 2 | 4 | 2
Joe | Partners’ representative |  | 3 | 3 | 0

## RBS
Resource Breakdown Structure (RBS)

## WBS and Rough Estimations
* | WBS and Rough Estimates
# | Description | Required Resources | Most Likely | Min | Max | Avg. Dur./Work | Budget Estimation
0 | The PMzone Digital Board Game |  | 182 | 124 | 285 | 160.5 | 40000
1 | Project Planning |  | 21 | 12 | 42 | 18.5 | 2000
1.1 | Game Requirements |  | 15 | 8 | 30 | 12.8333
1.2 | Project Plan |  | 6 | 4 | 12 | 5.6667
2 | Design Game |  | 35 | 26 | 60 | 33.1667 | 13000
2.1 | Functional Design |  | 10 | 8 | 20 | 10.3333
2.2 | Technical Design |  | 5 | 3 | 10 | 4.5
2.3 | UI/UX |  | 20 | 15 | 30 | 18.3333
3 | Develop Game |  | 60 | 43 | 85 | 52.8333 | 20000
3.1 | Player's Functionalities |  | 25 | 18 | 35 | 22
3.2 | Instructor's Functionalities |  | 20 | 15 | 30 | 18.3333
3.3 | Admin's Functionalities |  | 15 | 10 | 20 | 12.5
4 | Test Game |  | 66 | 43 | 98 | 56 | 5000
4.1 | Player's Functionalities Tests |  | 18 | 12 | 25 | 15.1667
4.2 | Instructor's Functionalities Tests |  | 18 | 12 | 25 | 15.1667
4.3 | Admin's Functionalities Tests |  | 18 | 12 | 25 | 15.1667
4.4 | UI/UX Tests |  | 5 | 3 | 10 | 4.5
4.5 | Technical Tests |  | 7 | 4 | 13 | 6
5 | Go-Live & Support |  | 0 | 0 | 0 | 0
5.1 | Training |  |  |  |  | 0
5.2 | Marketing |  |  |  |  | 0
5.3 | Operations |  |  |  |  | 0
5.4 | Support |  |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Gantt Chart
| PROJECT NAME: | PROJECT START: | WEEK FORMAT: | NON-WORKING DAYS:
| THE PMZONE DIGITAL BOARD GAME | 2021-03-01 | 1 | Fr | Sa | time axis 2021-02-24 to 2022-04-10
# | Task | Start Date | Duration | Finish Date | Person Responsible | % Complete | time axis 2021-02-24 to 2022-04-10
1 | Phase I: Project Planning | 2021-03-01 | 21 | 2021-03-21 |  | 57.14%
1.1 | Specify requirements | 2021-03-01 | 6 | 2021-03-07 |  | 80%
1.2 | Plan the project | 2021-03-08 | 5 | 2021-03-14 |  | 80%
1.3 | Write a Projejct Compass Document | 2021-03-08 | 4 | 2021-03-11 |  | 80%
1.4 | Perform a peer review of the compass document | 2021-03-14 | 4 | 2021-03-17 |  | 0%
1.5 | Approve project plan | 2021-03-18 | 2 | 2021-03-21 |  | 0%
1.6 | Compass document approved | 2021-03-18 | 0 | 2021-03-18 |  | 0%
1.7 | Project planning phase complete | 2021-03-22 | 0 | 2021-03-22 |  | 0%
2 | Phase II: Design Game | 2021-03-23 | 31 | 2021-04-22 |  | 0%
2.1 | Specify functional requirements | 2021-03-23 | 5 | 2021-03-28 |  | 0%
2.2 | Specify technical requirements | 2021-03-29 | 4 | 2021-04-01 |  | 0%
2.3 | Create wireframe mockups | 2021-04-04 | 6 | 2021-04-11 |  | 0%
2.4 | Design UI/UX | 2021-04-12 | 6 | 2021-04-18 |  | 0%
2.5 | Conduct DR (design review) with a focus group | 2021-04-19 | 3 | 2021-04-21 |  | 0%
2.6 | Design approved | 2021-04-22 | 0 | 2021-04-22 |  | 0%
2.1 | Game design phase completed | 2021-04-25 | 0 | 2021-04-25 |  | 0%
3 | Phase III: Develop Game | 2021-04-26 | 65 | 2021-06-29 |  | 0%
3.1 | Create development plan | 2021-04-26 | 4 | 2021-04-29 |  | 0%
3.2 | Approve development plan | 2021-05-02 | 3 | 2021-05-04 |  | 0%
3.3 | Develop Players’ functionalities | 2021-05-05 | 20 | 2021-05-24 |  | 0%
3.4 | Develop Instructors’ functionalities | 2021-05-25 | 15 | 2021-06-08 |  | 0%
3.5 | Develop Admins' functionalities | 2021-06-09 | 10 | 2021-06-20 |  | 0%
3.6 | Perform development tests | 2021-06-21 | 8 | 2021-06-28 |  | 0%
3.7 | Game functionalities developed | 2021-06-29 | 0 | 2021-06-29 |  | 0%
3.8 | Game development phase completed | 2021-06-30 | 0 | 2021-06-30 |  | 0%
4 | Phase IV: Test Game | 2021-04-26 | 92 | 2021-07-26 |  | 0%
4.1 | Create test plan & scenarios | 2021-04-26 | 15 | 2021-05-10 |  | 0%
4.2 | Approve test plan | 2021-05-11 | 5 | 2021-05-16 |  | 0%
4.3 | Perform Players' functional tests | 2021-06-30 | 15 | 2021-07-14 |  | 0%
4.4 | Perform Instructors’ functional tests | 2021-06-30 | 15 | 2021-07-14 |  | 0%
4.5 | Perform Admins’ functional tests | 2021-06-30 | 15 | 2021-07-14 |  | 0%
4.6 | Perform UI/UX tests | 2021-07-11 | 4 | 2021-07-15 |  | 0%
4.7 | Perform technical tests | 2021-07-12 | 8 | 2021-07-20 |  | 0%
4.8 | Review test reports | 2021-07-21 | 4 | 2021-07-25 |  | 0%
4.9 | All tests completed | 2021-07-26 | 0 | 2021-07-26 |  | 0%
4.1 | Game testing phase completed | 2021-07-27 | 0 | 2021-07-27 |  | 0%
5 | Phase V: Go Live & Support | 2021-04-26 | 109 | 2021-08-12 |  | 0%
5.1 | Create marketing & operation plan | 2021-04-26 | 5 | 2021-05-02 |  | 0%
5.2 | Develop training materials | 2021-07-01 | 8 | 2021-07-08 |  | 0%
5.3 | Develop marketing materials | 2021-05-03 | 8 | 2021-05-10 |  | 0%
5.4 | Transfer game to hosting | 2021-07-28 | 1 | 2021-07-28 |  | 0%
5.5 | Perform Go-Live tests | 2021-07-29 | 4 | 2021-08-01 |  | 0%
5.6 | Approve marketing & operation plan | 2021-08-02 | 2 | 2021-08-03 |  | 0%
5.7 | Approve training guide | 2021-08-04 | 2 | 2021-08-05 |  | 0%
5.8 | Approve marketing messages | 2021-08-08 | 2 | 2021-08-09 |  | 0%
5.9 | Review test reports | 2021-08-10 | 2 | 2021-08-11 |  | 0%
5.10 | Go-Live tests completed | 2021-08-12 | 0 | 2021-08-12 |  | 0%
5.11 | Go-Live & Support phase completed | 2021-08-15 | 0 | 2021-08-15 |  | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Formulas:
PROJECT START: = MIN([PROJECT START:, row below]:C10)
PROJECT START: = IF(WEEKDAY([NON-WORKING DAYS:, row above],D2)=6,[NON-WORKING DAYS:, row above]+2,IF(WEEKDAY([NON-WORKING DAYS:, row above],D2)=5,[NON-WORKING DAYS:, row above]+3,[NON-WORKING DAYS:, row above]+1))
NON-WORKING DAYS: = MAX([NON-WORKING DAYS:, row below]:E10)
NON-WORKING DAYS: = IF([WEEK FORMAT:]<>0,IF(WEEKDAY([PROJECT START:]+[WEEK FORMAT:]-1,D2)=6,[PROJECT START:]+[WEEK FORMAT:]+1,IF(WEEKDAY([PROJECT START:]+[WEEK FORMAT:]-1,D2)=7,[PROJECT START:]+[WEEK FORMAT:],[PROJECT START:]+[WEEK FORMAT:]-1)),[PROJECT START:])

## Communication Plan
Communication Plan
Communication Channel | Description | Participant/Recipients | Frequency | Reporting Format | Summary Format | Chanel Format
Project Status Meeting | Tracking the project's overall progress: closely tracking all work packages and milestones, solving any problems and difficulties that develop in the course of the project, making any necessary decisions regarding the project’s progress and implementation, resolving risks and other issues affecting the efficient implementation of the project's work plan, ensuring the project maintains its boundaries and quality. | Project Manager, Focus Group Team Leader | Weekly | Project log | Project log | Meeting
Development Status Meeting | Tracking the project's design and development and addressing functional and technical issues. | Project Manager, Focus Group Team Leader, Development Team Leader, Design Team Leader, QA Leader | Weekly | Periodic Status Report | Project log | Meeting
Focus Group Review Meeting |  | Project Manager, Focus Group Members, Marketing Consultant | Once every two weeks | Periodic Status Presentation (including mockups and working software) | Project log | Meeting
Technical Review Meeting |  | Project Manager, Focus Group Team Leader, Development Team Leader, Technical Consultant | Once every two weeks | Periodic Status Report | Project log | Meeting
Marketing Brainstorming Meeting |  | Project Manager, Focus Group Team Leader, Marketing Consultant | Once every two weeks | Periodic Status Report | Project log | Meeting

## Common Risks
* | Common Risks
# | Risk Description | Risk Response
1 | Fear that the development company will decide to change the terms of service and will not agree to transfer the code of the game to us | Securing rights in contract and maintaining periodic backup with us throughout the period of development and day-to-day operation
2 | Fear of difficulties connecting to the game in real time due to various internet glitches | Provide real-time support and communicate this risk to clients
3 | Fear of losing game reports due to technical glitch | Game report would be sent to Admin’s and to instructors right after each game
4 | Fear of leaking sensitive information out of the game due to hacking | No sensitive information will be stored within the game
5 | Fear of declining game value due to theft by hackers | Secure game against hacking and creating a reputation for the game associated with us
6
7
8
9
10
11